| Smokefree Multi-Unit Housing Policy Implementation: Sample Timeline |  |
| --- | --- |
| 2-4 months out | - Contact local county health department, public health organization, or smokefree property management company for advice/assistance - Choose a transition plan: - Example: Effective date for all current and new residents will be January 1st - Develop the policy – include: - Where smoking is and is not allowed - Who the policy applies to (tenants, guests, staff, service persons) - Definition of smoking - Effective date(s) *The American Lung Association recommends: - A policy that makes all units in the building smokefree. - A policy that extends to outdoor areas, such as playgrounds and pools, as well as decks, balconies, patios, etc. - A 100% smokefree grounds policy! If this is not feasible, then the policy should specify a minimum distance of 25 feet from all structures on the property. |
| 2 months out | - Review existing smokefree lease addendums (if available) and select language/addendum to use - Review sample enforcement plans (if available) and decide on a plan |
| 45 days out | - Give residents notice* - Order signage/stickers - Post flyers announcing tenant meeting |
| 1 month out | - Hold tenant meeting (Optional; now or two weeks out) - Property Manager to explain why they are going smokefree and explain lease addendum - Invite local public health organization to offer information for residents who would like to quit smoking - Residents have option to sign the new addendum at end of meeting (or by two weeks out in the office) - (Optional) Begin drafting press release with quotes from local public health organization(s) |
| Two weeks out | - Post signage at properties |
| “In Effect Day” | - New lease addendum in effect for current and new residents - (Optional) Press release out - Update advertising to include “smokefree building/property” amenity |

* Most states require that landlords give at least 30 days notice; check your state’s landlord-tenant law for more information.  Additional time gives residents a chance to get used to the change, making compliance easier.